## 1.1
		PROJECT NAME: MeatMe.com
	Test Script Name:	MeatMe Test Script		T/S #:			TS-0001
	Test Case Description	Login
	Test Case Reference No:	1
	Scenario/Purpose:	Check ability to register/login with valid email and password
	Test Cases Verified:	3
	Requirements Verified:
	Prerequisites:	Developed MeatMe Web Application
	Name of Tester:	Ruth Byrd				Date:
	Build Number:	1				Time:
Step	Description	Expected Results	Actual Results	Pass	Fail	N/A	Defect/Comments
1	Validate link availability	IE, Chrome, FF opens	Link is available	P
2	Go to home page	MeatMe web window displays	home page displays	P
3	Registration	Click login to display the login page	page displays	P
4	create new user	click on register as a new user	registration page displays	P
5	registration page functionality	1. Enter email address ruthlbyrd@gmail.com and password: “P@$$w0rd” confirm password 2. Click enter	returns to home page	P
6	registration attempt with same uid and password	1. Enter email address ruthlbyrd@gmail.com and password: “P@$$w0rd” confirm password 2. Click enter	name ruthlbyrd@gmail.com is already taken email ruthlbyrd@gmail.com is already taken	P			Illegible text mauve on cocoa background no warning sound
	End of Test Case

## 1.2
		PROJECT NAME: MeatMe.com
	Test Script Name:	MeatMe Test Script		T/S #:			TS-0001
	Test Case Description	Search from the Home Page
	Test Case Reference No:	1
	Scenario/Purpose:	Check pork search function
	Test Cases Verified:	3
	Requirements Verified:
	Prerequisites:	Developed MeatMe Web Application
	Name of Tester:	Ruth Byrd				Date:
	Build Number:	1				Time:
Step	Description	Expected Results	Actual Results	Pass	Fail	N/A	Defect/Comments
1	Validate link availability	IE, Chrome, FF opens		P
2	Go to home page	1. Click on Login 2. MeatMe web site login window displays 3. Enter UID and password 4. Greeting appears on home page		P
3	Search by pork	1. Click drop down box for 'pork chops' 2. Cut name page should display 3. Click Back to List to return to Home page	1. Cut name page displays with 'edit| back to list' options		F		Edit should not be visible/ functional for the user
4	Return results for existing Cut Name	Pork data: retail cut, primal cut, alternative name, and cooking methods are displayed; Back to List returns user to the Home page	1. Click Back to List 2. The Retail Cuts page displays 3. Click on details link, that returns the user to the Cut name page		F		.The user is not able to return to the Home page or the Search List as is intended.
	End of Test Case

## 1.3
		PROJECT NAME: MeatMe.com
	Test Script Name:	MeatMe Test Script		T/S #:			TS-0001
	Test Case Description	Search from the Home Page
	Test Case Reference No:	1
	Scenario/Purpose:	Check beef search function
	Test Cases Verified:	3
	Requirements Verified:
	Prerequisites:	Developed MeatMe Web Application
	Name of Tester:	Ruth Byrd				Date:
	Build Number:	1				Time:
Step	Description	Expected Results	Actual Results	Pass	Fail	N/A	Defect/Comments
1	Validate link availability	IE, Chrome, FF opens		P
2	Go to home page	1. Click on Login 2. MeatMe web site login window displays 3. Enter UID and password 4. Greeting appears on home page		P
3	Search by beef	1. Click drop down box for 'sirloin steak' 2. Cut name page should display 3. Click Back to List to return to Home page	1. Cut name page displays with 'edit| back to list' options		F		Edit should not be visible/ functional for the user
4	Return results for existing Cut Name	1. Beef data: retail cut, primal cut, alternative name, and cooking methods are displayed; 2. Back to List returns user to the Home page	1. Click Back to List 2. The Retail Cuts page displays 3. Click on details link, that returns the user to the Cut name page		F		The user is not able to return to the Home page except using the main menu
	End of Test Case

## 1.4
		PROJECT NAME: MeatMe.com
	Test Script Name:	MeatMe Test Script		T/S #:			TS-0001
	Test Case Description	Restricted Access User Test
	Test Case Reference No:	1
	Scenario/Purpose:	Various search filter criteria and display results
	Test Cases Verified:	3
	Requirements Verified:
	Prerequisites:	Developed MeatMe Web Application
	Name of Tester:	Ruth Byrd				Date:
	Build Number:	1				Time:
Step	Description	Expected Results	Actual Results	Pass	Fail	N/A	Defect/Comments
1	validate user restrictions	choose beefMe type	1. displays sirloin steat cut name page 2. “edit|back to list” is not restricted and is visible to the user		F		Edit should not be visible for the user
2	verify admin only edit ability on the edit page	1. From Cut Name page user is requested to login once 'edit' is clicked 2. user should be denied access to edit function	1. edit page displays; 2. Changed steat to steak and primal cut drop down from loin to chuck 3. Click Save to display “retail cuts page”		F		This functionality was designated as restricted during all requirements gathering and is fully functional to every user upon login feature.
3	verify admin only edit ability on the retail cuts page	Create new' functions should not be functional to the user only the admin	1. Create new functions are visible and functional to the user 2. Enter Pork Chops/Loin and click save 3. Returns the user to the Retail cuts page detail		F
4	verify admin only details ability on the retail cuts page	Details' functions should not be visible/functional to the user only the admin	Click on details and Cut name page displays with the details of the cut of meat		F		The user is not able to return to the Home page except using the main menu
5	verify admin only delete ability on the retail cuts page	Delete' functions should not be visible/functional to the user only the admin	Click on delete displays the delete page Appropriate confirm delete message Click delete bacon is removed		F

	End of Test Case

## 1.5
		PROJECT NAME: MeatMe.com
	Test Script Name:	MeatMe Test Script		T/S #:			TS-0001
	Test Case Description	Search Box
	Test Case Reference No:	1
	Scenario/Purpose:	Various search filter criteria and display results
	Test Cases Verified:	3
	Requirements Verified:
	Prerequisites:	Developed MeatMe Web Application
	Name of Tester:	Ruth Byrd				Date:
	Build Number:	1				Time:
Step	Description	Expected Results	Actual Results	Pass	Fail	N/A	Defect/Comments
1	Results for string in Alternative Names section	Identify a string that exists in the Alternative Names section of a recipe but NOT in the Primal Cut Name section	retail cuts detail has top sirloin as alternative name for Sirloin Steak	P
2	String with 2 characters / (Also tests string can be part of larger string)	1. enter 'to' of top sirloin alternative name to sirloin steak 2. click on search 3.Sirloin steak cut name page is displayed.	Results in UI match results in database	P
3	Search with no value	1. Do not enter a value in search box / 2. Click Search appropriate err msg displays	Displays the retail cuts page		F
4	String does not appear in any records	Enter string: abc123 / Click Search Message: No results.	“cut not found” is displayed	P

	End of Test Case